## Sheet1
Task | Week 1 Jan 23-Jan 29 | Week 2 Jan 30-Feb 5 | Week 3 Feb 6 - Feb 12 | Week 4 Feb 13- Feb 19 | Week 5 Feb 20 - Feb 26 | Week 6 Feb 27 - Mar 4 | Week 7 Mar 5 - Mar 11 | Week 9 Mar 12 - Mar 18 | Week 9 Mar 19 - Mar 25 | Week 10 Mar 26 - Apr 1 | Week 11 Apr 2 - Apr 8 | Week 12 Apr 9 - Apr 15 | Week 13
Use Case Design and Requirements | P, D, G
ERD
UI Design Drawings | S, Z, G, W
UI Tech Investigation (Sample Code) | Z
Data Structure Design (Class Diagram) |  | P, W
Data Structure Implementation (Code) |  |  | P
Data Structure QA (Test Code) |  |  | P
Database Design(Schema) | [5 empty] | P
Database Implementation | [6 empty] | P
Datastructure Serialization (code) | [6 empty] | P
Serialization QA code | [6 empty] | P
UI Page Implementation (Code) |  |  | Z |  |  | W, Z
Backend Coding |  |  |  | W |  |  |  | W
Integration Testing | [5 empty] | D
Functional Testing |  |  |  |  | D | [5 empty] | D
Architecture Design |  | Z, P, W | [9 empty] | D
Integration |  |  |  |  | P |  |  |  |  | P
Create Test Plan |  |  | D
P - Prannoy
D - Diana
G - George
S - Suhn
Z - Zhipeng
W - Wei
Note on G1: DianaA: Final date for March 8th Capstone Presenation
Note on D8: DianaA: Test code can be created in parallel development
Note on G9: DianaA: Not a priority task for March 8th Presentation
Note on D13: DianaA: UI Development for March 8th presentation to stop here. Development can continue for the project.