## R&R
FUNCTIONS
| Diana Alexander | Prannoy Tank | Zhipeng Zeng | Wei Liu | Suhn Kim | Sponsor(Dan Eng) | Rob Robson
ACTIVITIES
1.1 Project Management | R |  |  |  |  | C |  | R | Responsible
1.2.Use Cases | A | R | A | A |  | I | C | A | Accountable
1.3.UI Design | I | A | I | A | R | I | C | C | Consult
1.4 UI Development(coding) | I | A | R | A |  | I | C | I | Inform
1.5 Backend Development | I | A | A | R |  | I | C
1.6 Datastructure and Database Design | I | R | A | A |  | I | C
1.7 Project Testing | R | A | A | A |  | I | C
1.8 Architecture Diagram | I | R | A | A |  | I | C

## Risks
Risk | Impact | Probability | IxP | Ranking | Mitigation Plan (top 3 risks)
The architecture designed is not sound enough to accommodate all necessary components | 7 | 4 | 28 | 1 | Responsible team member must regularly compare the architecture design with the project requirements, and consult with the project sponsor Rob, to ensure that the designing progresses on the right track.
Requirements may change at the last minute | 8 | 5 | 40 | 2 | Requirements and scope have to be documented and frozen in advance. Scope Review to be done every 3 weeks to ensure work done is in scope.
The web app is not completed on time due to some unforseen issues | 8 | 4 | 32 | 3 | The delivery date will have to be extended or the team members might have to put in extra hours to meet the deadline. The project scope can also be reduced in this scenario.
The team might discover that the tools and software that they have decide use to build the webapp are not as effective as expected. | 9 | 3 | 27 | 4 | Discussions and research has to be done to come up with fixes and work arounds to meet project goals.
Team members may be unavailable due to unexpected issues | 5 | 3 | 15 | 5 | Other team members might be able to take up the responsibility of the missing team member.
Team may loose all data or coding done | 10 | 1 | 10 | 6 | Team will have to begin development from the scratch. The scope and final deliverable might have to be reduced or the project delivery date might have to be extended.

## Final Scope
Capstone 2016 - Story Board
Scope Statement
This project will involve creating a web application that will provide a graphical user interface[GUI] for the user to create stories. An XML file representing the story inclusive of all aspects of the story will be generated. The XML file can then be used as an input to Humber's game engine. The GUI design will provide user with options to set an environment, create scenes, select characters, dialogs and other preferences for the story The team will also create an architecture diagram, that will represent the big picture, demonstrating how the application integrates with other components that may be added on to the application at a later stage. Not all of the requirements and features will be implemented in this project.The final web application built, will be deployed on the server provided by the sponsor. The team members are to put in between 7-10 hours of work per week for the purpose of this project. This project will be completed by April 20, 2016 with one major deliverable on March 8th, 2016
Note on B4: DianaA: add that not everything wll be implemented

## Team Member Information
Name | cell | Role | email
Project Team
Dan Eng | 416-895-3238 | Project Sponsor | Dan.Eng@humber.ca
Rob Robson |  | Project Sponsor | Rob.Robson@humber.ca
Diana Alexander | 519-709-7496 | Project Manager | dia.alexander@gmail.com
Prannoy Tank | 647-504-7807 | Team Leader | prannoy23@gmail.com
Wei Liu | 416-821-8246 | Project Team Member | liuwei.lvvl@gmail.com
Zhipeng Zeng | 416-857-6107 | Project Team Member | keviniszzp@gmail.com
Suhn Kim |  | Project Team Member | kim.suhnmi@gmail.com
George Pervantes |  | Project Team Member | george.paravantes@humber.ca
COVE
Andre Asplung |  | andre.asplund@bell.ca
Steve Gorman
Note on A27: Maja Hjalmarsson Heather Rose

## Rough scope
Scope Statement | This project will involve creating a web application that will provide a graphical user interface[GUI] for the user to create stories. An XML file representing the story inclusive of all aspects of the story will be generated. The XML file can then be used as an input to Humber's game engine. The GUI design will provide user with options to set an environment, create scenes, select characters, dialogs and other preferences for the story The team will also create an architecture diagram, that will represent the big picture, demonstrating how the application integrates with other components that may be added on to the application at a later stage. Not all of the requirements and features will be implemented in this project.The final web application built, will be deployed on the server provided by the sponsor. The team members are to put in between 7-10 hours of work per week for the purpose of this project. This project will be completed by April 20, 2016 with one major deliverable on March 8th, 2016
Business objectives | Business need/opportunity/objectives
To create a web application that provides a Graphical User Interface through which game and animation students at Humber College can generate XML files which will then be given as input to Humber's game engine
To develop an architecture diagram, that will represent the big picture, demonstrating how the application integrates with other components that may be added on to the application at a later stage.
Team members to be graded for capstone based on their performance through the project
What is in
Develop the architecture diagram
Develop the web application with the desired graphical user interface.
Application will be usable on Google Chrome
User will be able to save his/her created stories in the database which can then be accessed by loging into the web application
Basic security, i.e. encrypted password will be saved in the database and user will be sent a forgot password link to reset password, will be provided
What is out
No language apart from English language will be supported by the web application
Web application does not provide support for wearable devices
Web application will not support any other XML schema apart from the one used in the application.
Risk |  | The architecture designed is not sound enough to accommodate all necessary components
The team might discover that the tools and software that they have decided use to build the web application are not as effective as expected.
The web app is not completed on time due to some unforseen issues
Requirements may change at the last minute
Team members may be unavailable due to unexpected issues
Team may loose all data or coding done
Project Estimates | High-level budget | Since this is an internal capstone project, we will not consider a bugdet for this project.
Stakeholders |  | Humber College - animation department including students and faculty
Rob Robson
Dan Eng
Project Team
Pedro Serrador
Project Team |  | Dan Eng - Project Sponsor
Rob Robson - Project Sponsor
Diana Alexander - Project Manager
Prannoy Tank - Team Leader
Wei Liu - Team Member
Zhipeng Zeng - Team Member
Suhn Kim - Team Member
George Paravantes - Team Member
Authorization |  | Dan Eng

## Learning Outcomes
Learning Outcomes | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Wei
working in a team environment, gaining experiences in developing complex software, using design patterns | Week 1: Understanding SourceTree, Intellij idea; Week 2: Research for web design, understanding XML designs
Zhipeng
gaining experiences in UI design in a higher level, front-end developing | Week 1: Research in UI technologies like dragula, Css3 library (animate.cs); Week 2: Compared different javascript frameworks, Researched Angularjs
Prannoy
working in a team environment, learning design pattern, thinking critical | Week 1: research in development technologies, Github set up; Week 2: researched Hibernate, EJB
Diana
managing project management, break-down structure | Week 1: learnt how to use Producteev; Week 2: Learnt how to use Trello, Toggl, created WBS; Week 3: Learnt how to break down project delivery with demo, WBS; Week 4: Learnt project tracking, tracking people with difficult to match schedules, scope review meetings to ensure that project is in scope

## High Level WBS
| Milestones | Dates | Comments
1.1 Project Management | Project Management Plan | 2016-01-30
1.1.2 Develop Project Plan | Architecture Diagram Complete | 2016-02-27
1.1.3 Develop Scope Statement | Use Cases Documentation | 2016-02-05
1.1.4 Scope Statement Approval | UI Design Complete | 2016-01-29
1.1.5 Status Meetings | UI Development Complete | tbd
1.1.6 Manage Time Log | Backend coding complete | tbd
1.1.7 Project Tracking | Testing complete | 2016-04-15 | tbd
1.2 Architecture Design | Capstone Presentation- March8th | 2016-03-08
1.2.1 Requirements Gathering | End of term Capstone Presentation | 2016-04-20 | tbd
1.2.2 Use Case Diagrams | Final capstone grading | 2016-04-21 | tbd
1.2.3 ERD
1.3 Design Datastructure and Database Schema
1.3.1 Data Structure design (Class diagrams)
1.3.2 Data Structure Implementation (code)
1.3.3 Data Structure QA (test code)
1.3.4 Database Design (schemas)
1.3.5 Databbase Implementation
1.3.6 Data Structure Serialization (code)
1.3.7 Serialization QA (code)
1.4 UI/UX
1.4.1 UI Design (Drawings)
1.4.2 UI Page implementation (code)
1.4.3 UI Tech Investigation (Sample code)
1.5 Backend Development
1.5.1 Integration
1.6 Testing
1.6.1. Functional Testing
1.6.2 Integration Testing

## Ownership in the Line (hidden)
Green Light Session
Objective: Cement the process in the line.
What do we need to do to make this happen?
Phased Approach:
Phase 1 - Continue to heighten awareness - (12 months)
Phase 2 - Identify training requirements and do training - (12 months)
Phase 3 - Hand off your process role to line and you will act as a consultant - (6 months)
Phase 4 - New environment fostered - Who are you - find another job.
Include as responsibility/accountability on ICA/OBJ with associated measures.
Include in Job Models
Recognize training requirements - facilitation, overview of process (RBG)
Entrench in group meetings process and gaps (broken items)
At section level communicate importance of process and that the responsibility lies at the section,
team and individual.
Re-focus process from Tier C to D to E
Develop a template checklist that recognizes how to fix the process
Put pressure on employees to keep process in their face
Increase the energy and desire to work on process
Anyone should be able to address/identify gaps
Recognize skill levels in section to educate members on what a gap looks like
Monthly Themed Communication Seminars
Feb - Process Prime Communication Plan
Mar - Customers, who they are and how to identify their needs Prime Dave McKenna
Apr - Gaps
May - Measures
Jun - CSA
Jul - Scorecard
Aug - Leading and Lagging Measures
Sep - Maps
Oct - Section Business Plan
Nov - Job Models
Dec - Year End Review
Plan is to have a prime per month who will develop the initial communication seminar package
and each prime will manipulate to meet their section needs.
Feb will be scoped out on Feb 11 meeting
Dave M will send out his AIO (March package) for discussion on Feb 11

## CSA Requirements (hidden)
Target Group (who is it and why do it) | Prime | DueDate | Measures
NCC Target Ntwk focus in NCC | Murray | Nov | Decrease in overdue orders and decrease in change orders by NCC Tech
Sales (MCS) - quality of MCIP packages | Murray | Nov
IS/IT - Support documentation without funding | Murray | Nov
This could be a process gap Gerry to investigate |  | June
BFCO - response time re commissioning | Gerry B | Dec | Remove extended time frame (improve cycle time of completed job)
IS&P group ??? | Brian | Dec | Brian will update by end of Feb
NDI - re service manager response for funding | Brian | Dec
Ntwk Mtce -they do provisioning in the field | Brian | Dec
LPAG - turn around times | Brian | Dec
Data shop - turn around and response time | Brian | Dec
Capacity Mgmt - response/product/communication | Brian | Dec
Expertech - quality of service - response time | Brian | Dec
NIC & FOM - quality audits - set the parameters | Brian | Dec
NCR - quality and response time | Brian | Dec
NPCO - (project mgmt grp) handoffs and timing not | Brian | Dec
FMS - new service intro | Brian | Dec
NSRC - quality | Brian | Dec
Transport - firm up the reservation of T1 links and | Dave | Dec | Completed
define reservation policy (perhaps closing the
process gap - common understanding)
Traffic Ntwk Mgmt - evaluate initial CSA | Anne | Dec
If enhanced CSA required (timing and handoffs
between Traffic and Ntwk Mgmt (Switch and Access) |  | Dec

## Agenda 01-20 (hidden)
District Process Team Meeting
| Date: | 2003-01-20
| Time: | 9:30 | to | 12:05
Conference Bridge #:
Chair Person #:
Participant #:
| Facilitator: |  | Dave
| Time Keeper: |  | Anne
| Note Taker: |  | Ryan
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:00 | 9:30 | 9:30 | Welcome and Review Agenda | All | Information Sharing
2 | 0:05 | 9:30 | 9:35 | Review Norms | All | Information Sharing
3 | 0:05 | 9:35 | 9:40 | Review Agenda Items | All | Information Sharing
4 | 0:05 | 9:40 | 9:45 | Review minutes of last meeting | All | Information Sharing
5 | 0:15 | 9:45 | 10:00 | Action Register | All | Discussion
6 | 0:45 | 10:00 | 10:45 | Support Implementation Design Project | Larry | Information Sharing
7 | 0:15 | 10:45 | 11:00 | Break
8 | 0:10 | 11:00 | 11:10 | Business Plan | All | Discussion
9 | 0:15 | 11:10 | 11:25 | Create a Mandate | All | Discussion
10 | 0:20 | 11:25 | 11:45 | Create Norms | All | Discussion
11 | 0:10 | 11:45 | 11:55 | Discuss Items Surrounding the Agenda ie. Locked in Items | All | Discussion
12 | 0:05 | 11:55 | 12:00 | Review Last Meeting | All | Discussion
13 | 0:05 | 12:00 | 12:05 | Review "Risk" presentation Training | All | Discussion
14 |  | 12:05 | 12:05
15 |  | 12:05 | 12:05
16 |  | 12:05 | 12:05
17 |  | 12:05 | 12:05
18 |  | 12:05 | 12:05
19 |  | 12:05 | 12:05
20 |  | 12:05 | 12:05
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 01-20 (hidden)
Meeting Minutes
Facilitator: | Dave | Notetaker: | Ryan | Timekeeper: | Anne
Attendees:
Dave | Ryan | Anne | Murray | Larry
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Review Minutes of last meeting | 1) Develop Risk Presentation - In progress. 2) Ryan to update Action Register with meeting agendas and meeting minutes. 3) To keep visibility within the District, the District Process Team will publish their work quarterly within a Power Point Presentation. Ryan is to insert an empty presentation file within the Process folder on the O drive. 4) The District Process Team will send a formal invitation to the other sections that are currently not represented at the meetings.
L2 Redefine | 1) Design Phase is complete. 2) Currently working on the Implementation Design Phase. 3) Defined Corporate vs. Local Application and Major vs. Minor Application. 4) Created a list of all the support committees.
Business Plan | 1) Team has decided to use our Action Register as our Business Plan. This will keep everything within one document. Consequently a "BP" field will be added to the Action Register to flag items that are Business Plan related.
Agenda Items | 1) There are 3 items that will make a regular monthly appearance on the agendas. They will be "Review the Minutes of the Last Meeting", "Action Register", "Quarterly District Meeting Updates".
Create a Mandate | 1) Ladies and gentlemen we have an new mandate… Check the "Mandate" TAB within this document
Create Norms | 1) Discussed and agreed on a set of Meeting Norms to be used during each meeting. Check the "Meeting Norms" TAB within this document.
Date of Next Meeting: |  | 2003-02-10
Roles For Next Meeting:
Facilitator: | Ryan | Notetaker: | Anne | Timekeeper: | Murray
Meeting Evaluation: |  | Good, Concise, To the point

## Agenda 02-10 (hidden)
District Process Team Meeting
| Date: | 2003-02-10
| Time: | 9:30 | to | 12:00
| Location: |  | Room:
|  | Conference Bridge #: |  | 1-866-540-8130
Chair Person #:
|  | Participant #: |  | 6270925#
| Facilitator: |  | Ryan
| Time Keeper: |  | Murray
| Note Taker: |  | Anne
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:05 | 9:30 | 9:35 | Welcome and Review Agenda | All | Information Sharing
2 | 0:05 | 9:35 | 9:40 | Review Norms | All | Information Sharing
3 | 0:05 | 9:40 | 9:45 | Review Agenda Items | All | Information Sharing
4 | 0:10 | 9:45 | 9:55 | Review minutes of last meeting | All | Information Sharing
5 | 0:15 | 9:55 | 10:10 | Action Register | All | Discussion
6 | 0:20 | 10:10 | 10:30 | Talk about the action register - do we want all of these tabs. (What's with the long file name.) | Team | Discussion
7 | 0:15 | 10:30 | 10:45 | Break
8 | 0:20 | 10:45 | 11:05 | L2 Redefine | Larry | Information Sharing
9 | 0:25 | 11:05 | 11:30 | Risk Presentation | Dave | Discussion
10 | 0:30 | 11:30 | 12:00 | Tier D Scorecard | Ryan | Information Sharing
11 |  | 12:00 | 12:00
12 |  | 12:00 | 12:00
13 |  | 12:00 | 12:00
14 |  | 12:00 | 12:00
15 |  | 12:00 | 12:00
16 |  | 12:00 | 12:00
17 |  | 12:00 | 12:00
18 |  | 12:00 | 12:00
19 |  | 12:00 | 12:00
20 |  | 12:00 | 12:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 02-10 (hidden)
Meeting Minutes February 10 2003
Facilitator: | Ryan | Notetaker: | Anne | Timekeeper: | Murray
Attendees: | Ryan, Dave, Anne & Murray
Regrets (Absent): | na
AGENDA ITEM | NOTES/ACTION REQUIRED
5 The Action Register | Mechanized Scorecard; Ryan provided an update on the Transport District's mech scorecard (Steve Scott Tools & Measures prime) status. Transport is currently utilizing the tool for Department/District Tactical reporting only, currently not usable for Tier D/E Objective Perfromence Reporting. Action: Ryan to request a presentation by Steve Scott at the next Process Pals Mtg March 10 with focus on 2 items i) selling/marketing the automated tool ii) what the benefits would be to transfer to this tool for a District with functional Scorecards already in place Ryan confirmed Feb 12 of Steve's availability for March 10 F2F - location is Creekbank (if that suits everyone).
Risk Presentation; this item is Parked until discussion with Joanne Doust re Department involvement Update Feb 12; Dave & Anne met with Joanne & determined roles & responsibilities. Dave will issue a copy of our little Risk Presentation to the reps in Transport etc & they can determine if it is what they wanted or, if those primes need to develop their own. Joanne to confirm email distribution contacts. Action; Dave to issue Risk Presentation to this distribution Raoul W. etc.
6 The Action Register Format | Action; Ryan to 'hide" 2002 closed/historical items and only keep current tabs viewable including current month +1 and ii) Ryan to create a tab to contain the Process Pals 2003 Mandate
8 Redefine Project | Update from Larry; slides now posted to Process folder O drive + emailed Feb 11. Larry provided Redesign url address http://sarnet.qc.bell.ca/redefine_support/. All presentations located on this website. New communication package under development & will be available later this week. No action items for the Process Pals this week.
1 Review Minutes from Jan meeting | Action; Murray to follow up with BB/IP teams to determine if they want to send a member to this forum
Date of Next Meeting:
March 10, 2003
Roles For Next Meeting:
Facilitator: | Anne | Notetaker: | Murray | Timekeeper: | Dave
Meeting Evaluation: |  | good - shorter than planned!

## Agenda 03-10 (hidden)
District Process Team Meeting
| Date: | March 10, 2003
| Time: | 10:00 | to | 12:00
| Location: |  | Room: | n/a
|  | Conference Bridge #: |  | 1-866-540-8130
Chair Person #:
|  | Participant #: |  | 6256724#
| Facilitator: |  | Anne
| Time Keeper: |  | Murray
| Note Taker: |  | Dave
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:05 | 10:00 | 10:05 | Welcome & Review Agenda | Anne
2 | 0:25 | 10:05 | 10:30 | Review Feb 10 Minutes | all
3 | 0:15 | 10:30 | 10:45 | Review & Update Action Register | all
4 | 0:15 | 10:45 | 11:00 | L2 Redefine Project Update | Larry B.
5 | 0:15 | 11:00 | 11:15 | BREAK | all
6 | 0:15 | 11:15 | 11:30 | Updates for District Process Web site | Murray
7 | 0:15 | 11:30 | 11:45 | Plan Apr 3rd F2F Process Mtg | all
8 |  | 11:45 | 11:45
9 |  | 11:45 | 11:45
10 |  | 11:45 | 11:45
11 |  | 11:45 | 11:45
12 |  | 11:45 | 11:45
13 |  | 11:45 | 11:45
14 |  | 11:45 | 11:45
15 |  | 11:45 | 11:45
16 |  | 11:45 | 11:45
17 |  | 11:45 | 11:45
18 |  | 11:45 | 11:45
19 |  | 11:45 | 11:45
20 |  | 11:45 | 11:45
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 03-10 (hidden)
Meeting Minutes March 10, 2003
Facilitator: | Anne | Notetaker: | Murray | Timekeeper: | Dave
Attendees: | Dave, Anne & Murray
Regrets (Absent): | Ryan
AGENDA ITEM | NOTES/ACTION REQUIRED
5 The Action Register | Mechanized Scorecard; Ryan provided an update on the Transport District's mech scorecard (Steve Scott Tools & Measures prime) status. Transport is currently utilizing the tool for Department/District Tactical reporting only, currently not usable for Tier D/E Objective Perfromence Reporting. Action: Ryan to request a presentation by Steve Scott at the next Process Pals Mtg March 10 with focus on 2 items i) selling/marketing the automated tool ii) what the benefits would be to transfer to this tool for a District with functional Scorecards already in place Ryan confirmed Feb 12 of Steve's availability for April 03/03 @ 10am F2F - location is Creekbank (if that suits everyone).
Risk Presentation; this item is Parked until discussion with Joanne Doust re Department involvement Update Feb 12; Dave & Anne met with Joanne & determined roles & responsibilities. Dave will issue a copy of our little Risk Presentation to the reps in Transport etc & they can determine if it is what they wanted or, if those primes need to develop their own. Joanne to confirm email distribution contacts. Action; Dave to issue Risk Presentation to this distribution Raoul W. etc. Dave presented to Transport Process Mgrs & Assocs Mar 03/903. Well received. Dave to followup with J.Doust re. closing the loop on this topic.
6 The Action Register Format | Action; Ryan to 'hide" 2002 closed/historical items and only keep current tabs viewable including current month +1 and ii) Ryan to create a tab to contain the Process Pals 2003 Mandate. CLOSED.
8 Redefine Project | Update from Larry; slides now posted to Process folder O drive + emailed Feb 11. Larry provided Redesign url address http://sarnet.qc.bell.ca/redefine_support/. All presentations located on this website. New communication package under development & will be available later this week. No action items for the Process Pals this week. Larry presenting to Tier Bs today Mar 10/03. Update to follow.
1 Review Minutes from Jan meeting | Action; Murray to follow up with BB/IP teams to determine if they want to send a member to this forum Murray to send minutes to Charles & Jim.
Ryan | Ryan to find Jan/03 minutes and put into XLS. file (new tab)
Ryan | Ryan determine Steve Scott's requirements for Apr/03 meeting. Is there anything that the Process team needs to do prior ??
Date of Next Meeting:
April 03, 2003
Roles For Next Meeting:
Facilitator: | Murray | Notetaker: | Dave | Timekeeper: | Ryan
Meeting Evaluation: |  | MV - productive. AM - no bagels. DM - good.

## Agenda 04-03 (hidden)
District Process Team Meeting
| Date: | 2003-04-03
| Time: | 10:00 | to | 3:00PM
| Location: |  | Room: | Creekbank Room CB2 (lower level)
Conference Bridge #:
Chair Person #:
Participant #:
| Facilitator: |  | Murray
| Time Keeper: |  | Ryan
| Note Taker: |  | Dave
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 1:00 | 10:00 | 11:00 | Steve Scott presentation | Ryan
2 | 0:45 | 11:00 | 11:45 | Create Bus Plan for 2003 | All
3 | 0:30 | 11:45 | 12:15 | How do we make ourselves more public - raise profile ?? | Dave
4 | 0:30 | 12:15 | 12:45 | Lunch | All
5 | 0:15 | 12:45 | 13:00 | Minute taker must send note to Jerome each month | TBD
6 | 0:30 | 13:00 | 13:30 | Update on web page | Murray
7 | 0:30 | 13:30 | 14:00 | Larry update (confirm time slot) | All
8 |  | 14:00 | 14:00
9 |  | 14:00 | 14:00
10 |  | 14:00 | 14:00
11 |  | 14:00 | 14:00
12 |  | 14:00 | 14:00
13 |  | 14:00 | 14:00
14 |  | 14:00 | 14:00
15 |  | 14:00 | 14:00
16 |  | 14:00 | 14:00
17 |  | 14:00 | 14:00
18 |  | 14:00 | 14:00
19 |  | 14:00 | 14:00
20 |  | 14:00 | 14:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 04-03 (hidden)
Meeting Minutes April 3, 2003
Facilitator: | Murray | Notetaker: | Dave | Timekeeper: | Ryan
Attendees:
Regrets (Absent): | Larry Benedet
AGENDA ITEM | NOTES/ACTION REQUIRED
1 | Mechanized Scorecard (Steve Scott Tools & Measures prime) Steve Scoot gave a presentation of the automated (TNI) Transport Scorecard. It was noted that the TNI scorecard can drill down to tier “D” and therefore the individual can understand and appreciate how their personal activates impact the district scorecard. As well in the future it will be used with regards to the Objective Performance for “tier” “D”. Next Steps for the process pals – talk to Gord – how can we adapt this to our section(s). Is there anything here we can use. ACTION ITEM: Ryan to engage Gord Lange and establish "next steps" from a mechenization perspective. ACTION ITEM: Dave to get .ppt from Steve and he link to their scorecard. Continue investigating using the TNI type of scorecard. At least get it into access. Gord can call Steve anytime. Other team members – Brad Jones, Kristin Lucy.
2 | It was agreed by the team that the process bus plan for 2003 will not be created - we will use the action register as the BP.
3 | First quarter .PPT - what we have done – what we are working on etc. One page high-level .PPT for “C” and “B”. The team created a .PPT at the meeting. Ryan to create the .PPT and send to the team to review.
6 | Process WEB page (Murray) is being updated by no one at this time (i.e. their is not a prime) – Murray is going to talk with Andrew Chin and let the team know if he can do the updates on the WEB page. Ryan to see if he can take a course on building WEB pages then he could make the updates for us – Ryan to update for next meeting.
ONMP – are their users in our district that this will affect. I.e. are their impacts with our teams. Action Item: Each of the process pals to send a note to their section asking for any impact. Send the .PPT but be sure that in the body of the note that TARS is being replaced. They may want to go to their TARS support person if they want input.
Mics | One of the process pals (not to be name here) mentioned that it might be appropriate to bring “more” than 20 timbits.
Date of Next Meeting: |  | May 12, 2003
Roles For Next Meeting:
Facilitator: | Dave | Notetaker: | Ryan | Timekeeper: | Anne
Meeting Evaluation:
Note on C13: David McKenna: Gord to give our team an update as to moving our scorecard to the dbase. (By end of May for assessment – how does it work today, i.e. how many people working on the scorecard today versus tomorrow)
Note on C15: David McKenna: First quarter process update – send this to Ryan (he will send to the PP first to review) List our mandate Ryan. · Developed risk presentation – rollout in qtr 2 and 3. · Evaluate Automated balanced scorecard solution. · Assisted with the OSS definition for the NP Redefine Project. · Development of CSA between o Translations and NCC. o Switch with access.

## Agenda Jun-09 (hidden)
District Process Team Meeting
| Date: | 2003-06-09
| Time: | 9:00 | to | 10:30
| Location: |  | Room: | n/a
|  | Conference Bridge #: |  | 416-343-2578 or 866-235-8288
Chair Person #:
|  | Participant #: |  | 7565052 #
| Facilitator: |  | David
| Time Keeper: |  | Murray
| Note Taker: |  | Anne
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:05 | 9:00 | 9:05 | Welcome & Review Agenda | David
2 | 0:25 | 9:05 | 9:30 | Review April 10 Minutes | all
3 | 0:15 | 9:30 | 9:45 | Review & Update Action Register | all
4 | 0:10 | 9:45 | 9:55 | L2 Redefine Project Update | David
5 | 0:10 | 9:55 | 10:05 | Updates for District Process Web site | Murray
6 | 0:10 | 10:05 | 10:15 | Risk Assessment Update | All
7 | 0:15 | 10:15 | 10:30 | Open items | All
8 |  | 10:30 | 10:30
9 |  | 10:30 | 10:30
10 |  | 10:30 | 10:30
11 |  | 10:30 | 10:30
12 |  | 10:30 | 10:30
13 |  | 10:30 | 10:30
14 |  | 10:30 | 10:30
15 |  | 10:30 | 10:30
16 |  | 10:30 | 10:30
17 |  | 10:30 | 10:30
18 |  | 10:30 | 10:30
19 |  | 10:30 | 10:30
20 |  | 10:30 | 10:30
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes Jun-09 (hidden)
Meeting Minutes June 9, 2003
Facilitator: | Dave | Notetaker: | Anne | Timekeeper: | Murray
Attendees: | Dave, Ryan, Murray (sans laptop) & Anne
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
1 | Welcome & Review
2 | Review Previous Minutes: Enhanced Automated Scorecard Feasibility: Ryan & Gord met with Steve Scott/ next step understand all measures in District Section teams; waiting for new functionality of NP OTOV card; follow up with Gord to obtain NP OTOV timelines. Process Pals will then determine next steps & timelines
3 | Review & Update Action Register: Dave updated the Action Register
4 | L2 Redefine: Roadshow rolled out to Ottawa Tier C's, London rollout scheduled June 17, no info on Toronto schedule; Dave to obtain Roadshow Schedule from Larry
5 | Process District Web Site Status Update: Murray to set up impromptu mtg with Andrew Chin - Murray to advise netmtg date in June 2003.
6 | Risk Assessment Status Update: suggestion from Dave's rollout - have teams analyze all job function maps/tasks to determine if Risk applicable
7 | II QTR Communication Update: create the update via Wed July 9th at 1:30 conf call
Date of Next Meeting: |  | Sept 8, 2003
Roles For Next Meeting: |  | F2F
Facilitator: | Ryan | Notetaker: | Murray | Timekeeper: | Anne
Meeting Evaluation:

## Action Reg
| Live Action Register |  |  |  | Last Update:
[5 empty] | This Facilitator: |  |  | Diana Alexander
Next Facilitator:
# | Category | Issue Details/Action Plan | Issue Title | COMPLETION DATE | PRIME | Extended Team | COMMENTS | STATUS
1 | Setup | 1. Finish Git repository setting |  | Jan - 29 | Prannoy | Rob, Prannoy, Diana, Wei |  | Completed
2 | PM | 2. Requirement gathering (Diana, Prannoy, George) |  | Feb 5 | Prannoy | Diana, George | could not meet with George | Ongoing
3 | UI | 3. UI Design (George, Suhn, Wei) |  | Jan - 29 | Suhn | George, Wei | could not meet with George | Ongoing
4 | UI | 4. UI Technology Investigation (Zhipeng) |  | Jan - 29 | Zhipeng |  | dosnt allow components to connect. Zhipeng recommends angular JS | Completed
5 | Architecture | 5. MVP (Rob) |  | Jan - 29 | Rob |  | Rob absent for the meeting | Open
6 | UI | 6. UI Drawings to be Scanned |  | Jan - 29 | Rob |  | Rob absent for the meeting | Open
7 | Dev | Technologies to be confirmed |  | Jan - 29 | Prannoy | Rob, Wei, Zhipeng | Will be confirmed by email since Rob was absent. UI technologies, java script libraries to be clarified | Open
8 | PM | Scope statement approval |  | Jan - 29 | Dan | Diana |  | Open
9 | PM | Learning Outcomes Meeting |  | Jan - 29 | Diana | Prannoy, Wei, Zhipeng |  | Open
10 |  | New WBS Approval |  |  | Dan | Diana
11 |  | XML designs to be clarified |  |  | Prannoy
12 |  | UI Screens for the Demo to be decided |  | Feb 5 | Zhipeng
13 |  | Architecture status |  | Feb 5 | Prannoy |  | does it need more work? If yes, what?
14 |  | a question arose; should ‘Dialogue’ belong to ‘Character’ or ‘Scene’? |  | Feb 5 | Prannoy, Zhipeng
15 |  | People with learning disablilties - dialogs should be talked out |  |  |  |  | datasturcture must allow for this
16 |  | xml representation
17 |  | Datastructure Diagram and implementation |  | Feb 12 | Prannoy |  | is implementation required now?
18 |  | architecture structure review |  | Feb 12 | Rob |  |  | Open
19 |  | One more screen for timeline to be added in future- George is working on it |  | March 9 | George, Rob |  |  | Open
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
|  |  |  | Open | Yes
|  |  |  | Ongoing | No
Completed

## PM notes
try to create a story to demo for capstone
| team to refer to inklewriter as a reference to develop website. | Action item
2016-02-12 | Zhipeng to continue with playground screen | task update in wbs and trello, send email - done
| don’t want to implement on mobile device - demo UI, anything for mobile device - | add to out of scope - done [push to github]
| XML - new version - | task complete in wbs and trello - done
| backend datastructure - | task update in wbs and trello - done
| team is going to use spring mvc and hibernate - | update flyer
| variables - what scene you go to based on variables | topic for future ref, add to action reg - visit again after March 8th
| datastructure implementation needs to be done | task update - done
| layout options - flow, scrolled, full, windowed - give user options | add to documentation - visit again after March 8th
| scrolling options, set the size of a screen, captions, navigations, | add to documentation - visit again after March 8th
| script defnitions- need to be worked on later | topic for future ref, add to action reg - visit again after March 8th
| unreal engine - to demo | to be looked into
language
roles definition
| model - name of a model inside the engine - is a string | inform hiren, discuss with prannoy - done
| architecture diag to be updated - prototype break it down | task assign to wei - done
| jsps to be done | task assign to prannoy - done as backend coding
| summary screen - do a simple design rob designed. Hiren and george can work on a better version for later | task assigned to wei and zhipeng - done
| multiple timeline in future | add to documentation - done
| for demo - only one timeline with branching | add to in scope - done
| prannoy datastructure - servlet, session layer | task assign to prannoy - done as backend coding
| wei, zhipeng web pages | task assign to wei and zhipeng -done
| one more screen will be added - george is working on it - after march 9th | add to action reg - done
| connect screens - prannoy | assign task - done as backend coding
| taslk to hiren about logo and name | Name - Ustoria - done

## assumptions & questions
What we know | What we think we know (Assumptoins) | What we don't Know (Questions) | <-- Who to ask | Prime to get answer | Date for answers | Open or answered
Technology to be used - J2EE, Session Model, HTML 5, ajax, Angular JS, Spring MVC |  |  | Zhipeng, Rob | Zhipeng investigating Dragula | Jan - 29th
What technology to use for coding - EJB | Hibernate to be used for database |  | Rob
| Data structure QA test code can be developed along with data structure implementation - code |  | Rob
| Sample images |  | George
|  | Final project presentation date - 15th April | Pedro
datastructure design patterns - factory |  |  | Rob
database - mysql
UI Technology to be used - javascript libraries

## CR
Change Request Log
Number | Description | Approved?

## Agenda 04-07 (hidden)
District Process Team Meeting
| Date: | 2003-04-04
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 04-07 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 05-12 (hidden)
District Process Team Meeting
| Date: | 2003-05-12
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 05-12 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 06-09 (hidden)
District Process Team Meeting
| Date: | 2003-06-09
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 06-09 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 09-08 (hidden)
District Process Team Meeting
| Date: | 2003-09-08
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 09-08 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 11-10 (hidden)
District Process Team Meeting
| Date: | 2003-11-10
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 11-10 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 12-15 (hidden)
District Process Team Meeting
| Date: | 2003-12-15
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 12-15 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation: