## March 8th Demo
Task | Week 1 Jan 23-Jan 29 | Week 2 Jan 30-Feb 5 | Week 3 Feb 6 - Feb 12 | Week 4 Feb 13- Feb 19 | Week 5 Feb 20 - Feb 26 | Week 6 Feb 27 - Mar 4 | Week 7 Mar 5 - Mar 11 | Week 9 Mar 12 - Mar 18 | Week 9 Mar 19 - Mar 25 | Week 10 Mar 26 - Apr 1 | Week 11 Apr 2 - Apr 8 | Week 12 Apr 9 - Apr 15 | Week 13
Use Case Design and Requirements | P, D, G | [5 empty] | P, D, G
UI Design for Demo |  |  | S, Z, G, W | S, G |  |  | S,G
UI Tech Investigation (Sample Code) | Z
XML Design Approval |  | P, W
UI Page Implementation (Code) |  |  |  | Z, W |  |  | Z, W
Architecture Design |  |  |  |  | P, W
Integration and basic UI testing | [5 empty] | P |  |  |  |  | P
Track team learning outcomes | D |  |  |  |  | D | D
Manage team time sheet entries | D | [5 empty] | D
Handouts for Demo |  |  | D
Create Business cards, team logo for the presentation |  |  |  | D
Get the list of employers attending the event |  |  |  |  | D
Power Point Presenatation for Demo | [5 empty] | D
Demo team's elevator pitch and resume |  |  | D
Team internal prep before the event (Review employers and possible pitches) - March 4th | [5 empty] | P, D, Z, W
Prepare demo Presentation to be given at the capstone event |  |  |  |  | D, Z
Prepare a list of possible questions and answers employers might ask |  |  |  | P, W, Z, D
Send out invitations to employers for capstone presentation |  |  |  | P,W,Z,D
Create ERD and Database Design (Schema) | [6 empty] | P
Data Structure Design (Class Diagram) |  |  | P |  |  |  |  | P
Data Structure Implementation (Code) | [8 empty] | P
Data Structure QA (Test Code) | [8 empty] | P
Database Implementation |  |  |  | P
Datastructure Serialization (code) | [8 empty] | W
Serialization QA code | [8 empty] | W
Backend Coding |  |  |  |  | P |  |  |  |  | W
Integration Testing | [10 empty] | P, D
Functional Testing | [10 empty] | P,D
Deploy application created on the Server | [12 empty] | P, W
Create Test Plan | [5 empty] | P
Track project progress in Trello | D | [5 empty] | D
Create Final reports to be submitted for the capstone project | [10 empty] | D
Create Learning Outcomes Report | [11 empty] | D
Create any required sign off documents for project Handover | [12 empty] | D
P - Prannoy |  | Tasks for Demo
D - Diana |  | Tasks for Project
G - George |  | Tasks that are in progress and not sure about
S - Suhn |  | Tasks scheduled for that time period completed
Z - Zhipeng
W - Wei
Note on G1: DianaA: Final date for March 8th Capstone Presenation
Note on H2: DianaA: Revisit and confirm requirements
Note on E3: DianaA: Suhn delivers 2 UI page designs every week
Note on E6: DianaA: UI Development for March 8th presentation to stop here. Development can continue for the project.
Note on H6: DianaA: Zipeng is responsible for this task. Wei will work on this task in Week 7. Prannoy and Wei will provide support when required
Note on F7: DianaA: Prannoy will be responsible for this task, and consult with Wei when required
Note on G16: DianaA: Team to meet and prep on March 4th
Note on J23: DianaA: Test code can be created in parallel development